## User stories
sl. # | User story | User story description | status | Assigned to | comments
| Hackathon objective | as an engineer, I need to ensure the we create an innovative solution that can parse the data from given data sources and process to generate a model to predict the ESG scores | In progress | Team
|  | As an engineer, I need to ensure I have acess to all sources that will help me with building a solution for the hackathon objective, so that, I can build a working solution. | Closed | Saritha
|  | as an engineer, I need to ensure the code repos are created in github to ensure deploymet is suucessful | Closed | Saritha
|  | As an engineer, I need to upload a pdf or other data files to the cloud storage to ensure the relevant data is available to build a schema so that the data mapping is available. | Closed | Team
|  | As an engineer, I need to create objects to store all schemas | Closed | Team
| Pdf parsing | As an engineer, I want to parse the data from the pdf versions so that the required indicators are gathered to process | Closed | Team
|  | As an engineer, I need to identify the AI services from the given data, so that the ESG benchmark details can be generated for the Firm to improve upon. | Closed | Team
As an engineer, I need to create an API that can generate a report with needed Indicator
|  | As an engineer, I need to create a Base model Microservice build and deploy to Cloud | Closed | Josh
|  | As an engineer, I need to find objects for the response | Closed | saritha
|  | As an engineer, I need to get end points to upload the pdf data file into the request | closed | josh
|  | As an engineer, I need to Run the API to ensure its working | Closed | Saritha
|  | As an engineer, I need to Deploy the API to the cloud | Closed | Saritha
| create Indexes | As an engineer, I want to create indexes based on the data that’s identified from pdf parsing so that the json can be structured to generate the required outcome | Closed | Saritha
|  | As an engineer, I need to Enable cloud API gateway for ESG survey reporting service | Not required | Pooja | Not required
|  | As an engineer, I need to create a cloud storage bucket | Closed | Pooja
|  | As an engineer, I need to Create a serviceaccount and key to ensure sufficient permissions / accesses are granted to commit | Closed | Saritha | Not required
|  | As an engineer, I need to Create new entity model by creating LLMs to feed the pdfs | Not started | Saritha | Vertex AI access issue was a blocker that we overcame from talking to GCP team and the Pes.
| User stories | As an engineer, I need to Document User Stories | Closed | Mani
| Test case Documentation | As an engineer, I need to Document test cases for success and failure scenarios | Closed | pooja
| Design Document | As an engineer, I need to Create a high level Solution Design document | Closed | Mani
| Code commit | As an engineer, I need to commit the code to the assigned Git repos | Closed | Team
| Test Coverage | As an engineer, I need to validate the code thru postman etc., | Closed | Team
| Playbook | As an engineer, I need to create a playbook to showcase the deployed solution and monitoring ' | Closed | Saritha

## Indicator mapping
question | esgType | esgIndicators | primaryDetails | secondaryDetails | citationDetails | pageNumber
ESG Risk Rating for MSCI | ESGScore | MSCISustainalytics |  |  | string
what is net zero target | Environment | NetZeroTarget |  |  | string | 0
what is the interim emission reduction target | Environment | InterimEmissionsReductionTarget |  |  | string
what is the Renewable Electricity Target | Environment | RenewableElectricityTarget |  |  | string
what is the Circularity Stratergy & targets | Environment | CircularityStratergy |  |  | string
what is the Diversity, Equity and Inclusion target | Social | DE&ITarget |  | string | string | 0
what is the employee health and Safety audit target | Goverance | HealthAndSafetyTarget |  | string | string
what is supply audit target | Goverance | SuppluAuditTarget |  | string | string | 0
SuppluAuditTarget | Reporting | GRI |  | string | string
what is the SASB rating | Reporting | SASB |  | string | string
what is the TCFD rating | Reporting | TCFD |  | string | string
is the entity focussing on ESG assurance | Reporting | Assurance